## Project Timeline
Team Tasks Timetable | Who's Involved | Aug 12 | Sept 12 | Oct 12 | Nov 12 | Dec 12 | Jan 13 | Feb 13 | Mar 13 | April 13 | May 13 | June 13 | July 13 | Aug 13 | Sept 13 | Oct 13 | Nov 13 | Dec 13 | Jan 14 | Feb 14
Action Areas
Workshops
Select locations | SE, JJ, RSDP
Form 8 local workshops | SE, JJ, RDSP
8 Regional F2C workshops | SE, RSDP, partners
Webinars with UMN SGE on how to engage schools with F2F activities and competition | PC, CNE's
Market workshops | All partners
Competition & Video
Notify stakeholders of competition | All partners
Launch competition video | MDE
Competition month | FFVP schools
Competition entry submission | FFVP schoos
Winners announced | SE,MDE, MDA
Evaluation
Develop survey for CNEs | SE, Kangting
Survey CNEs for baseline | SE, Kangting
Develop postF2C workshop evaluation | SE, Kangting
Survey F2C workshop participants | Partners
MDE tracking tool baseline $ MN Grown | MDE
MDE tracking tool post $ MN Grown | MDE
Baseline FFVPs schools using CNEs | UMN SGE
Post FFVPs schools using CNEs | UMN SGE
Team Tasks Timetable | Who's Involved | Aug 12 | Sept 12 | Oct 12 | Nov 12 | Dec 12 | Jan 13 | Feb 13 | Mar 13 | April 13 | May 13 | June 13 | July 13 | Aug 13 | Sept 13 | Oct 13 | Nov 13 | Dec 13 | Jan 14 | Feb 14
Action Areas
Reporting
Submit annual report 1 | Project Director
Submit annual report 2 | Project Director

## Workshops
Team Tasks Timetable | Who's Involved | Aug 12 | Sept 12 | Oct 12 | Nov 12 | Dec 12 | Jan 13 | Feb 13 | Mar 13 | April 13 | May 13 | June 13 | July 13 | Aug 13 | Sept 13 | Oct 13 | Nov 13 | Dec 13 | Jan 14 | Feb 14
Action Areas
Planning
Establish steerring committee
Form regional planning committee with 8 lead planning partners | SE, RSDP, __
Identify 1/2 metro leads
Workshop Details
Identify dates for each region (February 2013)
Establish content
Establish format
Identify host sites
Marketing
Funding food/meal
Print workshop material
Print promotional material
Webinar with SGE | UM Ext CFS, PC, CNEs
Develop material/content

## Competition and Video
Team Tasks Timetable | Who's Involved | Aug 12 | Sept 12 | Oct 12 | Nov 12 | Dec 12 | Jan 13 | Feb 13 | Mar 13 | April 13 | May 13 | June 13 | July 13 | Aug 13 | Sept 13 | Oct 13 | Nov 13 | Dec 13 | Jan 14 | Feb 14
Action Areas
Competition
Establish guidelines
Establish awards for school/farmer partnerships
Establish and confirm key messages
Post competition details on MDE website
Notify stakeholders of competition | All partners
Launch competition video | MDE
Competition month | FFVP schools
Competition entry submission | FFVP schoos
Winners announced | SE,MDE, MDA
Awards distibuted | SE,MDE, MDA
Plan school visits
Winning school visits
Video
Confirm budget | SE, MDE
Shoot #1 for competition and "teaste" video with Carrie | SE, Andrea, MDA
Plan and shoot a series of 3-4 nutriton promos with Carrie OPTION #B | SE, Andrea, MDA
Establish and confirm key messages for promos and "tease" video(s) | SE, Andrea

## Evaluation
Team Tasks Timetable | Who's Involved | Aug 12 | Sept 12 | Oct 12 | Nov 12 | Dec 12 | Jan 13 | Feb 13 | Mar 13 | April 13 | May 13 | June 13 | July 13 | Aug 13 | Sept 13 | Oct 13 | Nov 13 | Dec 13 | Jan 14 | Feb 14
Action Areas
Develop survey for CNEs | SE, Kangting
Survey CNEs for baseline | SE, Kangting
Reminders to CNEs to complete survey @ SGE conference | SE, Sue, Renee
Develop post F2C workshop evaluation (SurveyMonkey) | SE, Kangting
Survey F2C workshop participants | Partners
Modify tracking tool to extract competition information | MDE, Eval GA
MDE tracking tool baseline $ MN Grown
MDE tracking tool post $ MN Grown | MDE
Baseline FFVPs schools using CNEs | MDE
Post FFVPs schools using CNEs | UMN SGE