July 29, 2010

Draft Agreement for MISA’s Information Exchange program to fund:

Project Title: PROFILES IN SUSTAINABLE AGRICULTURE: A PROTOTYPE TECHNICAL CASE STUDY FOR BEGINNING FARMERS

Brief description of the project:

Today’s aspiring farmer is confronted with many sustainable agriculture resources, which generally fall into two categories: inspiring narratives and technical bulletins.  We developed a prototype case study on Loon Organics (Small market farm that markets primarily through Community Supported Agriculture and that integrated these two types of resources into a technical case study format.  The case study has been well-received, and we would like to add a second case, Clover Valley Farms.  Clover Valley Farms has been in operation for five years and several operational aspects make it a good case study:

The Clover Valley case study will profile Cindy Hale and Jeff Hall through a detailed narrative and provide embedded technical assistance via links to finance, production, and marketing resources.  The completed case study will be added to the Profiles in Sustainable Agriculture website: http://sustagprofiles.info/default.htm

This “one-shop stop” case study format would provide beginning and transitioning farmers with both a motivating story and the contextual understanding needed for integrating the nuts and bolts of sustainable farming into a real-life enterprise.

Project Lead:

Sarah Stai, Ecosmith Consulting

Collaborating Partners:

- UM Extension Small Farm Team: Betsy Wieland, Wayne Martin

- Renewing the Countryside (RTC): Jan Joannides, Brett Olson,

- Minnesota Institute for Sustainable Agriculture (MISA): Beth Nelson and Jane Grimsbo Jewett, intern (supervised by Sarah Stai and Beth Nelson)

- Clover Valley Farms: Cindy Hale and Jeff Hall

Budget and Budget Narrative:

| Personnel | Compensation | In-Kind |
| --- | --- | --- |
| EcoSmith Consulting 100 hours @ $50/hour: prototype coordination, technical writing | $5000 | n/a |
| Intern 60 hours @ $12/hour: photography and videography (including editing) | $720.00 |  |
| Clover Valley Farms (Cindy Hale and Jeff Hall) 20 hours @ $25/hour: interviews, farm tour, draft review | $500.00 | n/a |
| Reviewers 4 hours @ $25/hour x 6 reviewers (3 technical, 3 utility) | $600.00 | n/a |
| Advisory Committee (outside members) 3 members, 10 hours each @ $25/hour | $750.00 | n/a |
| Minnesota Institute of Sustainable Agriculture 3% FTE x 1 staff | n/a | n/a |
| University of MN Extension, Betsy Wieland, .01 FTE | n/a | $530 |
| Travel |  |  |
| Eco Smith Consulting 2-3 trips to Clover Valley Farms/Minneapolis, 310 miles per trip @ $0.50/mile | $500 | n/a |
| Intern, 2-3 trips to Clover Valley Farms/Minneapolis for filming and editing consultation | $500 | n/a |
| Total | $8,570.00 |  |

Preliminary Timeline for Clover Valley Farms Case Study—7/29/10

| Month | Tasks | People |
| --- | --- | --- |
| Early August | Hire intern Prepare agreements with EcoSmith and Clover Valley Farms (CV) Refine timeline Set up Advisory Committee (AC)* | Beth, Sarah Beth, Sarah, Cindy Sarah, Cindy, Intern Beth, Sarah, AC |
| August | Background research/prep for visit Farm visit #1** for photos, videos, and initial interview Organize notes/footage (Finalize Loon Organics video) | Sarah Sarah, Intern, CV Sarah, Intern Sarah, Intern, Jane? |
| September | Follow-up interviews (phone or email) Farm visit #2 Organize notes/footage Draft case study | Sarah, Cindy Sarah, Intern, CV Sarah, Intern Sarah |
| October | Research resources/links Farm visit #3 Edit photo/video Draft #1 to AC for review | Sarah, Betsy Sarah, Intern, CV Intern Sarah, AC |
| November | Arrange peer reviewers Incorporate AC comments Draft #2 to CV for review Incorporate CV comments | Beth, Sarah Sarah Sarah, Cindy Sarah |
| December | Draft #3 to peer reviewers (PR) Incorporate PR comments Final draft to AC and CV Publish PDF and Web site | Beth, Sarah Sarah Sarah, AC, Cindy Sarah, Intern, Jane |

*AC = Beth (MISA – project oversight), Jan (Renewing the Countryside - storytelling), Betsy (UM-Extension – resources); others = Wayne (UM-Extension), Nick Olson (LSP-Farm Beginnings), Jerry Ford (SFA-MN), Emily Hoover (UM - Dept. of Horticulture)?

**Anticipate 1-3 trips based on seasonal events we may want to capture on photo/video:

- "On farm" processing dates include:

  - July 30th (ducks)

  - August 6-7th (Cornish broilers)

  - Sept 17-18th (red broilers)

  - late October (turkeys)

- Hogs are processed off site the end of October.

- Tree fruit harvest can begin in late August but usually in Sept. and cider pressing in late Sept/early Oct.

Deliverables:

Sarah will work with intern and coordinate with MISA to ensure posting of the written prototype case study (to include narrative, photos, and links to resources and video) to their respective Web sites.  Sarah will also provide a PDF version of the case study to project team members for circulation and later use in grant writing.

The case study will be available online, and will be able to be used and accessed by others, and used in training sessions with attribution.  This case study can eventually be used in a database of case studies being planned or integrated into the current databases of the partner organizations.

Invoicing:

Sarah will invoice MISA on a monthly basis for time spent on farm visit(s), meetings, and writing and coordination tasks and for mileage reimbursement.  MISA will pay intern hours and reimburse travel costs, as invoiced by intern.

Other partners and peer reviewers will invoice MISA at project end.